## WBS and Gantt
STG-455 Production Release Engineering for a Cross Platform Mobile Application: Work Breakdown Structure and Gantt Chart (Term One)
Edit blue/yellow cells only. Enter actual finish dates in the Actual finish column as tasks complete. Costs and tools follow the team BOM; see the Assumptions sheet for sources and the legend.
[15 empty] | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
ID | Milestone / Task | Resources | People | Duration (workdays) | Predecessors | Successors | Start | Finish | Labor hours | Direct cost: team budget | Direct cost: paid by Studio XE | Total cost | Actual finish | Status | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14
M1 | Project Onboarding and Requirements |  |  | 24 |  |  | 2026-09-28 | 2026-10-29 | 282 | 0 | 0 | 0 |  | In progress
1.1 | Project onboarding, NDAs, and kickoff | Team Lead, Members A-C; Studio XE sponsor | 4 | 5 | None | 1.2 | 2026-09-28 | 2026-10-02 | 60 | 0 | 0 | 0 | 2026-10-02 | Complete - on time
1.2 | Obtain access to Studio XE source repositories (GitHub), staging backend, and test accounts | Team Lead; Studio XE sponsor (1-5 business days after NDA) | 2 | 8 | 1.1 | 1.3, 1.5, 2.1 | 2026-10-05 | 2026-10-14 | 48 | 0 | 0 | 0 |  | In progress
1.3 | Analyze app architecture and all 19 screens | Members A-C; Studio XE source code | 3 | 4 | 1.2 | 1.4 | 2026-10-15 | 2026-10-20 | 36 | 0 | 0 | 0 |  | Not started
1.4 | Complete requirements and technology review | Team Lead, Members A-C | 4 | 4 | 1.3 | 1.6, 6.1 | 2026-10-21 | 2026-10-26 | 48 | 0 | 0 | 0 |  | Not started
1.5 | Learn required technologies (Expo EAS, Sentry, Maestro, GitHub Actions) | Members A-C; vendor documentation | 3 | 6 | 1.2 | 1.6, 2.2 | 2026-10-15 | 2026-10-22 | 54 | 0 | 0 | 0 |  | Not started
1.6 | Establish development plan and confirm tools | Team Lead, Members A-C | 4 | 3 | 1.4, 1.5 | 3.1, 5.1 | 2026-10-27 | 2026-10-29 | 36 | 0 | 0 | 0 |  | Not started
M2 | Developer Accounts and Early Store Submission |  |  | 18 |  |  | 2026-10-15 | 2026-11-09 | 90 | 0 | 124 | 124 |  | Not started
2.1 | Get access to the partner Apple Developer, Google Play Console, and Expo accounts | Team Lead, Member A; Studio XE pays $99 Apple and $25 Google fees | 2 | 3 | 1.2 | 2.2 | 2026-10-15 | 2026-10-19 | 18 | 0 | 124 | 124 |  | Not started
2.2 | Configure EAS Build, signing credentials, and first minimal build | Member A, Member B; partner Expo organization (EAS); Xcode and Android Studio | 2 | 5 | 2.1, 1.5 | 2.3, 3.1, 4.1 | 2026-10-23 | 2026-10-29 | 30 | 0 | 0 | 0 |  | Not started
2.3 | Submit minimal build to TestFlight and Google Play internal testing | Member A, Member B; developer accounts | 2 | 2 | 2.2 | 2.4, 6.3 | 2026-10-30 | 2026-11-02 | 12 | 0 | 0 | 0 |  | Not started
2.4 | Monitor store review (Beta App Review 24-48 hours; first Google Play review up to 7 days) and address feedback | Member A, Member B; developer accounts | 2 | 5 | 2.3 | None | 2026-11-03 | 2026-11-09 | 30 | 0 | 0 | 0 |  | Not started
M3 | Crash and Error Reporting |  |  | 12 |  |  | 2026-10-30 | 2026-11-16 | 90 | 0 | 0 | 0 |  | Not started
3.1 | Integrate Sentry React Native SDK in the app | Member B, Member C; partner Sentry organization; app source code | 2 | 5 | 1.6, 2.2 | 3.2, 3.3 | 2026-10-30 | 2026-11-05 | 30 | 0 | 0 | 0 |  | Not started
3.2 | Configure reporting for all build configurations (development, preview, production) with source map upload from EAS builds | Member B, Member C; EAS build profiles | 2 | 4 | 3.1 | 3.4, 3.5 | 2026-11-06 | 2026-11-11 | 24 | 0 | 0 | 0 |  | Not started
3.3 | Enable Sentry PII scrubbing so reports exclude personal, financial, and health data | Member C; Sentry settings | 1 | 2 | 3.1 | 3.4, 3.5 | 2026-11-06 | 2026-11-09 | 6 | 0 | 0 | 0 |  | Not started
3.4 | Write triage process and runbook | Member B, Member C | 2 | 3 | 3.2, 3.3 | 7.1, 8.2 | 2026-11-12 | 2026-11-16 | 18 | 0 | 0 | 0 |  | Not started
3.5 | Verify reporting with test crashes on both platforms | Member B, Member C; test devices | 2 | 2 | 3.2, 3.3 | None | 2026-11-12 | 2026-11-13 | 12 | 0 | 0 | 0 |  | Not started
M4 | Build-and-Submit Pipeline |  |  | 14 |  |  | 2026-10-30 | 2026-11-18 | 90 | 0 | 0 | 0 |  | Not started
4.1 | Define EAS build profiles and automate signing credential handling | Member A, Member B; EAS | 2 | 4 | 2.2 | 4.2, 4.3 | 2026-10-30 | 2026-11-04 | 24 | 0 | 0 | 0 |  | Not started
4.2 | Create single-command build-and-submit for iOS and Android | Member A, Member B; EAS Build and Submit; Node.js and EAS CLI | 2 | 5 | 4.1 | 4.4, 5.4 | 2026-11-05 | 2026-11-11 | 30 | 0 | 0 | 0 |  | Not started
4.3 | Secure signing secrets used by the pipeline (GitHub secrets) | Member A; GitHub Actions secrets | 1 | 2 | 4.1 | 4.4 | 2026-11-05 | 2026-11-06 | 6 | 0 | 0 | 0 |  | Not started
4.4 | Document the pipeline | Member A, Member B | 2 | 3 | 4.2, 4.3 | 4.5 | 2026-11-12 | 2026-11-16 | 18 | 0 | 0 | 0 |  | Not started
4.5 | Validate the pipeline end to end from a clean checkout | Member A, Member B; test devices | 2 | 2 | 4.4 | 7.1, 8.2 | 2026-11-17 | 2026-11-18 | 12 | 0 | 0 | 0 |  | Not started
M5 | Automated Smoke Test in Continuous Integration |  |  | 22 |  |  | 2026-10-30 | 2026-12-02 | 147 | 0 | 0 | 0 |  | Not started
5.1 | Set up Maestro CLI (Java 17+) and a GitHub Actions workflow on the partner repository | Member C, Team Lead; GitHub Actions (partner-billed) | 2 | 3 | 1.6 | 5.2 | 2026-10-30 | 2026-11-03 | 18 | 0 | 0 | 0 |  | Not started
5.2 | Build test harness: staging test accounts (no production data) and stable testIDs | Member C, Member B; staging backend | 2 | 5 | 5.1 | 5.3 | 2026-11-04 | 2026-11-10 | 30 | 0 | 0 | 0 |  | Not started
5.3 | Write Maestro flows covering all 19 screens | Member C, Member B, Team Lead; Maestro CLI | 3 | 8 | 5.2 | 5.4 | 2026-11-11 | 2026-11-20 | 72 | 0 | 0 | 0 |  | Not started
5.4 | Run smoke test in CI on every pull request | Member C; GitHub Actions | 1 | 3 | 5.3, 4.2 | 5.5, 7.1 | 2026-11-23 | 2026-11-25 | 9 | 0 | 0 | 0 |  | Not started
5.5 | Stabilize flaky tests and document how to run them | Member C, Member B | 2 | 3 | 5.4 | 8.2 | 2026-11-30 | 2026-12-02 | 18 | 0 | 0 | 0 |  | Not started
M6 | OS and Device Support Matrix |  |  | 18 |  |  | 2026-10-27 | 2026-11-19 | 132 | 0 | 2500 | 2500 |  | Not started
6.1 | Identify current and two prior major iOS and Android versions; define matrix | Team Lead, Member C | 2 | 2 | 1.4 | 6.2 | 2026-10-27 | 2026-10-28 | 12 | 0 | 0 | 0 |  | Not started
6.2 | Purchase and set up developer phones (iPhone and Pixel); gather team members' older-iOS phones | Team Lead; Studio XE pays $2,500 for 2 phones (1-3 business days after approval) | 2 | 5 | 6.1 | 6.3 | 2026-10-29 | 2026-11-04 | 30 | 0 | 2500 | 2500 |  | Not started
6.3 | Run validation on physical devices, iOS Simulator, and Android emulators across the matrix | Members A-C; phones, Xcode, Android Studio; builds from pipeline | 3 | 8 | 6.2, 2.3 | 6.4 | 2026-11-05 | 2026-11-16 | 72 | 0 | 0 | 0 |  | Not started
6.4 | Document results and known issues in the support matrix | Member C, Team Lead | 2 | 3 | 6.3 | 8.2 | 2026-11-17 | 2026-11-19 | 18 | 0 | 0 | 0 |  | Not started
M7 | Store Acceptance (TestFlight and Google Play Internal Testing) |  |  | 9 |  |  | 2026-11-30 | 2026-12-10 | 54 | 0 | 0 | 0 |  | Not started
7.1 | Submit release candidate built by the pipeline to both stores | Member A, Member B; developer accounts | 2 | 2 | 4.5, 3.4, 5.4 | 7.2 | 2026-11-30 | 2026-12-01 | 12 | 0 | 0 | 0 |  | Not started
7.2 | Respond to store review feedback | Member A, Member B | 2 | 5 | 7.1 | 7.3 | 2026-12-02 | 2026-12-08 | 30 | 0 | 0 | 0 |  | Not started
7.3 | Confirm acceptance in both testing tracks and invite testers | Team Lead, Member A | 2 | 2 | 7.2 | 8.4 | 2026-12-09 | 2026-12-10 | 12 | 0 | 0 | 0 |  | Not started
M8 | Project Management, Quality Assurance, and Closeout |  |  | 57 |  |  | 2026-09-28 | 2026-12-17 | 279 | 261.84 | 0 | 261.84 |  | In progress
8.1 | Gantt chart updates and performance measurement (recurring); Claude Pro for 4 users, Term One months | Team Lead; Microsoft 365 (GCU); Claude Pro for each member | 1 | 57 | None | None | 2026-09-28 | 2026-12-17 | 171 | 261.84 | 0 | 261.84 |  | In progress
8.2 | Quality review of deliverables against acceptance criteria (runs alongside store review) | Members A-C | 3 | 5 | 6.4, 5.5, 3.4, 4.5 | 8.3, 8.4 | 2026-12-03 | 2026-12-09 | 45 | 0 | 0 | 0 |  | Not started
8.3 | Prepare handoff documentation for Term Two | Team Lead, Member C | 2 | 3 | 8.2 | 8.5 | 2026-12-10 | 2026-12-14 | 18 | 0 | 0 | 0 |  | Not started
8.4 | Prepare final presentation and physical-device demo | Members A-C; physical devices | 3 | 4 | 8.2, 7.3 | 8.5 | 2026-12-11 | 2026-12-16 | 36 | 0 | 0 | 0 |  | Not started
8.5 | Deliver final presentation and live demonstration | Members A-C; physical devices | 3 | 1 | 8.3, 8.4 | None | 2026-12-17 | 2026-12-17 | 9 | 0 | 0 | 0 |  | Not started
M9 | Class Assignments (CLC and Course Deliverables) |  |  | 48 |  |  | 2026-10-12 | 2026-12-18 | 678 | 0 | 0 | 0 |  | In progress
9.1 | Weekly Project Status Update (10/16) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-10-16 | 2026-10-16 | 6 | 0 | 0 | 0 |  | Not started
9.2 | CLC - Product Functional Requirements | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 6 | None | 9.5 | 2026-10-12 | 2026-10-18 | 72 | 0 | 0 | 0 |  | In progress
9.3 | CLC - Project Timeline and Work Breakdown Structure | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 3 | 4 | None | 9.5 | 2026-10-14 | 2026-10-18 | 36 | 0 | 0 | 0 |  | In progress
9.4 | Weekly Project Status Update (10/23) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-10-23 | 2026-10-23 | 6 | 0 | 0 | 0 |  | Not started
9.5 | CLC - Design Review Presentation 1 | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 6 | 9.2, 9.3 | 9.8 | 2026-10-16 | 2026-10-23 | 72 | 0 | 0 | 0 |  | Not started
9.6 | Peer Evaluation 1 | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 1 | None | None | 2026-10-23 | 2026-10-23 | 12 | 0 | 0 | 0 |  | Not started
9.7 | Weekly Project Status Update (10/30) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-10-30 | 2026-10-30 | 6 | 0 | 0 | 0 |  | Not started
9.8 | CLC - Project Portfolio | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 5 | 9.5 | 9.16, 9.22 | 2026-10-27 | 2026-11-01 | 60 | 0 | 0 | 0 |  | Not started
9.9 | Weekly Project Status Update (11/06) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-11-06 | 2026-11-06 | 6 | 0 | 0 | 0 |  | Not started
9.10 | October Expense Report | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 1 | 1 | None | None | 2026-11-08 | 2026-11-08 | 3 | 0 | 0 | 0 |  | Not started
9.11 | Weekly Project Status Update (11/13) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-11-13 | 2026-11-13 | 6 | 0 | 0 | 0 |  | Not started
9.12 | Weekly Project Status Update (11/20) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-11-20 | 2026-11-20 | 6 | 0 | 0 | 0 |  | Not started
9.13 | CLC - Updated Stakeholder Feedback | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 3 | None | 9.16 | 2026-11-19 | 2026-11-22 | 36 | 0 | 0 | 0 |  | Not started
9.14 | Weekly Project Status Update (11/27) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-11-27 | 2026-11-27 | 6 | 0 | 0 | 0 |  | Not started
9.15 | Weekly Project Status Update (12/04) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-12-04 | 2026-12-04 | 6 | 0 | 0 | 0 |  | Not started
9.16 | CLC - Final Design Concept Report | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 8 | 9.13, 9.8 | 9.19, 9.21, 9.23 | 2026-11-24 | 2026-12-06 | 96 | 0 | 0 | 0 |  | Not started
9.17 | November Expense Report | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 1 | 1 | None | None | 2026-12-06 | 2026-12-06 | 3 | 0 | 0 | 0 |  | Not started
9.18 | Weekly Project Status Update (12/11) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-12-11 | 2026-12-11 | 6 | 0 | 0 | 0 |  | Not started
9.19 | Design Solutions | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 3 | 9.16 | None | 2026-12-10 | 2026-12-13 | 36 | 0 | 0 | 0 |  | Not started
9.20 | Weekly Project Status Update (12/18) | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 2 | 1 | None | None | 2026-12-18 | 2026-12-18 | 6 | 0 | 0 | 0 |  | Not started
9.21 | CLC - Design Review Presentation 2 | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 6 | 9.16 | None | 2026-12-11 | 2026-12-18 | 72 | 0 | 0 | 0 |  | Not started
9.22 | CLC - Project Portfolio Revision | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 5 | 9.8 | None | 2026-12-14 | 2026-12-18 | 60 | 0 | 0 | 0 |  | Not started
9.23 | Initial Testing Plan | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 4 | 9.16 | None | 2026-12-15 | 2026-12-18 | 48 | 0 | 0 | 0 |  | Not started
9.24 | Peer Evaluation 2 | Team Lead, Members A-C; Microsoft 365 (Word, Excel, Teams) | 4 | 1 | None | None | 2026-12-18 | 2026-12-18 | 12 | 0 | 0 | 0 |  | Not started
| PROJECT TOTAL | [5 empty] | 2026-09-28 | 2026-12-18 | 1842 | 261.84 | 2624 | 2885.84
BUDGET CHECK
| Team budget limit (charter, covers both terms) | 4000
| Team cash cost allocated to Term One (Claude Pro) | 261.84
| Team budget remaining after Term One items | 3738.16
| Cash paid by Studio XE in Term One (accounts and developer phones) | 2624
SCHEDULE CHECK
| Term One end date | 2026-12-20
| Planned project finish | 2026-12-18
| Calendar days of slack before term end | 2
| Result | On schedule: finishes before term end
Note on N6: Actual finish 10/02/2026 per the project status report.

## Assumptions
STG-455 Project Timeline: Assumptions and Legend
Input | Value | Notes
Project start date | 2026-09-28 | Monday of the week the project began. The onboarding/NDA task is dated to match the status report (completed 10/02/2026).
Hours worked per person per workday | 3 | Estimate of unpaid student effort, used for the labor hours column. Change to match the team's real availability.
Claude Pro cost per license-month ($) | 21.82 | Source: team BOM (rev 1.0, 10/13/2026): $20.00 per user per month plus 9.1% Phoenix sales tax.
Team size (people) | 4 | Source: team BOM and status report (4 team members).
Term One months of Claude Pro | 3 | Assumption: Term One covers Oct-Dec 2026, 3 of the 7 months in the BOM (Oct 2026 - Apr 2027). The other 4 months fall in Term Two.
Team budget limit ($) | 4000 | Source: team BOM (charter limit). Covers both terms.
Term One end date | 2026-12-20 | Provided by the team. All Term One tasks must finish before this date (12/20/2026 is a Sunday, so the last workday is Friday 12/18).
Non-working days (excluded from schedule)
2026-11-26 | Thanksgiving | Only days before the 12/20/2026 term end are listed. Edit to match your course calendar; the schedule recalculates.
2026-11-27 | Day after Thanksgiving
ASSUMPTIONS
Durations are estimates in working days (Mon-Fri, excluding the non-working days above). Start and finish dates are formulas driven by predecessors, so changing a duration or predecessor moves every later task.
Class assignments (milestone M9) use the due dates from the course schedule provided by the team. Assignments already submitted before 10/13/2026 (Project Charter, Industry Standards, Stakeholder Feedback, BOM, and the 10/02 and 10/09 status updates) are not listed. Due dates are fixed inputs (11:59 PM); Start = due date minus the effort duration. Weekly participation posts are not listed because they need no project effort. Enter the submission date as the Actual finish to see early, on time, or late.
Resources use roles (Team Lead, Member A, B, C). Replace them with team member names once tasks are assigned.
Costs and tools come from the team BOM (STG-455-RS-BOM_StudioXE.xlsx, rev 1.0, 10/13/2026). Direct costs are split into the team budget and costs paid by Studio XE, as in the BOM. Team members are unpaid, so task costs are direct costs only; effort is tracked in the labor hours column.
Paid by Studio XE: Apple Developer Program $99 and Google Play Console $25 (task 2.1), and two developer phones, $1,250 each (task 6.2). Partner-provided services (EAS, Sentry, GitHub Actions, staging backend) and free tools are $0 to the project.
Team cost: Claude Pro for 4 users, allocated to the Term One months only (task 8.1). The full 7-month BOM cost is 28 license-months.
Lead times from the BOM are built into durations: partner repository and staging access 1-5 business days after the NDA, partner account access 1-2 business days, phones 1-3 business days after approval, TestFlight Beta App Review 24-48 hours, and a first Google Play review of up to 7 days.
Older iOS versions are covered by team members' phones and the iOS Simulator, and older Android versions by flashing the Pixel and using Android emulators (per the BOM).
Scope follows the project description for Term One only, which ends 12/20/2026. Term Two (offline cache, optimistic writes, shared components) is out of this timeline. The final demo in the BOM is 04/23/2027.
Successors are derived from the predecessor column. If you change a predecessor, update the successor column to match.
LEGEND
Blue text on yellow = input you should edit. Black text = formula or fixed label.
Gantt bar colors: dark blue = milestone summary; light blue = planned task; green = completed early or on time; red = completed late.
To record progress, enter the actual finish date in the Actual finish column of the WBS and Gantt sheet. The Status column then shows Complete - early, on time, or late.